## Custo & Margem (PT)
💰 PalopConnect — Análise de Custos e Margem
🟡 CÉLULAS AMARELAS (texto azul) = valores editáveis — actualize com os dados reais do seu fornecedor. Os cálculos de margem actualizam automaticamente.
⛔ CÉLULAS BRANCAS / VERDES = fórmulas automáticas — NÃO editar. Alterar estas células quebra os cálculos de margem, comissão e ponto de equilíbrio.
FASE 1 — Planos Portugal + Europa (Em vigor — Lançamento 18 de Maio)
Plano | Dados (GB) | Validade | Preço de Venda (€) [ACTUALIZAR] | Custo Grossista (€) [ACTUALIZAR] | Margem Bruta (€/un.) | Margem Bruta % | Custos Fixos Mensais (€) [ACTUALIZAR] | Ponto de Equilíbrio (un./mês) | Referência Concorrência (€) | vs. Concorrente Mais Barato | Comissão Parceiro (€/un.) | Margem Líquida Pós-Comissão (€) | Margem Líquida Pós-Comissão % | Descrição | Custo Grossista (USD) [ACTUALIZAR] | Código / Fornecedor
Chegada (ESIM Access) | 3 | 15 dias | 4.9 | 1.4596 | 3.4404 | 70.21% | 200 | 59 | 3.2 | 53.12% | 0.833 | 2.6074 | 53.21% | Ideal para chegadas e estadias curtas | 1.64 | PRC8B6GK2 (ESIM Access)
Essencial (ESIM Access) | 5 | 30 dias | 9.99 | 2.4297 | 7.5603 | 75.68% | 200 | 27 | 2.13 | 369% | 1.6983 | 5.862 | 58.68% | O plano mais popular — melhor relação qualidade-preço | 2.73 | PV0Q6PZ7G (ESIM Access)
Conforto (ESIM Access) | 10 | 30 dias | 14.9 | 5.0463 | 9.8537 | 66.13% | 200 | 21 | 3.2 | 365.6% | 2.533 | 7.3207 | 49.13% | Estadias mais longas, utilizadores frequentes de WhatsApp | 5.67 | P29FDU5TL (ESIM Access)
Liberdade (ESIM Access) | 20 | 30 dias | 22.9 | 9.7277 | 13.1723 | 57.52% | 200 | 16 | 3.49 | 556.2% | 3.893 | 9.2793 | 40.52% | Utilizadores intensivos, nómadas digitais, estadias longas | 10.93 | P6PBYX5G4 (ESIM Access)
ℹ️ Os custos grossistas são ESTIMATIVAS baseadas em taxas típicas de agregadores de eSIM na UE. Actualize a Coluna E com os custos reais da fatura do seu fornecedor. Custos fixos mensais (Coluna H) = alojamento + suporte + operações.
FASE 2 — Planos por Corredor PALOP (Expansão Planeada)
⚠️ Os planos de corredor requerem confirmação de cobertura de fornecedor separada por mercado. Os custos grossistas abaixo são estimativas de mercado — obtenha cotações reais antes de definir preços.
Mercado | Plano (GB) | Validade | Preço de Venda Recomendado (€) [ACTUALIZAR] | Custo Grossista Est. (€) [ACTUALIZAR] | Margem Bruta (€/un.) | Margem Bruta % | Concorrente Mais Barato ($) | Cobertura Confirmada? | Prioridade | Notas | Comissão Parceiro (€/un.) | Margem Líquida Pós-Comissão (€) | Margem Líquida Pós-Comissão % |  | Custo Grossista (USD) [ACTUALIZAR] | Código / Fornecedor
🇸🇹 São Tomé e Príncipe | 3 | 30 dias | 64.9 | 37.3444 | 27.5556 | 42.46% | $59 Nomad | Não | 1.ª | Mar azul — apenas 2 concorrentes. Só 3G — confirmar velocidade antes de comercializar. | 11.033 | 16.5226 | 25.46% |  | 41.96 | STP (sem actualização)
🇦🇴 Angola — Essencial (ESIM Access) | 3 | 15 dias | 49.9 | 22.1432 | 27.7568 | 55.62% | $19 Nomad | Não | 2.ª | Ponto de dor Zona 4 — argumento de marketing mais forte. €7.444/GB vs Vodafone. | 8.483 | 19.2738 | 38.62% |  | 24.88 | P1OKIKO93 (ESIM Access)
🇨🇻 Cabo Verde — Conforto (ESIM Card) | 5 | 30 dias | 49.9 | 22.1699 | 27.7301 | 55.57% | $49 Airalo | Não | 3.ª | Maior TAM (195K viagens). Preço ~€19 vs Airalo $49 por 10GB. | 8.483 | 19.2471 | 38.57% |  | 24.91 | ESIM Card
🇬🇼 Guiné-Bissau — Conforto (ESIM Access) | 5 | 30 dias | 34.9 | 17.0168 | 17.8832 | 51.24% | $15.99 Monty | Não | 4.ª | Volume baixo, concorrência limitada. Adição simples após CV e AO. | 5.933 | 11.9502 | 34.24% |  | 19.12 | CKH436 (ESIM Access)
🇲🇿 Moçambique — Conforto (ESIM Access) | 5 | 30 dias | 24.9 | 7.7252 | 17.1748 | 68.98% | $16.99 Saily | Não | 5.ª | Mercado mais competitivo. Saily a $1,70/GB. Ganhar pela comunidade, não pelo preço. | 4.233 | 12.9418 | 51.98% |  | 8.68 | MB048 (ESIM Access)
🇦🇴 Angola — Conforto (ESIM Access) | 5 | 30 dias | 69.9 | 42.2483 | 27.6517 | 39.56% |  | Não |  | Plano premium Angola. $47.47 custo grossista — margem apertada. | 11.883 | 15.7687 | 22.56% |  | 47.47 | PO7O41OJI (ESIM Access)
🇲🇿 Moçambique — Essencial (ESIM Access) | 3 | 15 dias | 14.9 | 4.6369 | 10.2631 | 68.88% |  | Não |  | Plano económico Moçambique. Custo baixo, boa margem. | 2.533 | 7.7301 | 51.88% |  | 5.21 | MB047 (ESIM Access)
🇬🇼 Guiné-Bissau — Essencial (ESIM Access) | 3 | 15 dias | 24.9 | 10.2083 | 14.6917 | 59% |  | Não |  | Plano económico GB. Mercado com pouca concorrência. | 4.233 | 10.4587 | 42% |  | 11.47 | CKH407 (ESIM Access)
🇨🇻 Cabo Verde — Essencial (ESIM Card) | 3 | 30 dias | 34.9 | 14.5693 | 20.3307 | 58.25% |  | Não |  | Plano económico CV. Fornecedor ESIM Card — confirmar fiabilidade. | 5.933 | 14.3977 | 41.25% |  | 16.37 | ESIM Card
FASE 3 — Planos Só Portugal (Alternativa cobertura nacional)
ℹ️ Planos cobertura apenas Portugal (não incluem roaming europeu). Custo grossista mais baixo — ideal para visitantes que ficam exclusivamente em território português.
Plano | Dados (GB) | Validade | Preço de Venda (€) [ACTUALIZAR] | Custo Grossista (€) [ACTUALIZAR] | Margem Bruta (€/un.) | Margem Bruta % | Custos Fixos Mensais (€) [ACTUALIZAR] | Ponto de Equilíbrio (un./mês) | Referência Concorrência (€) | vs. Concorrente Mais Barato | Comissão Parceiro (€/un.) | Margem Líquida Pós-Comissão (€) | Margem Líquida Pós-Comissão % | Descrição | Custo Grossista (USD) [ACTUALIZAR] | Código / Fornecedor
Chegada PT (ESIM Access) | 3 | 15 dias | 4.9 | 1.335 | 3.565 | 72.76% | 200 | 57 | 3.2 | 53.12% | 0.833 | 2.732 | 55.76% | Só Portugal — ideal para chegadas e estadias curtas | 1.5 | CKH1003 (ESIM Access)
Essencial PT (ESIM Access) | 5 | 30 dias | 9.9 | 2.1182 | 7.7818 | 78.6% | 200 | 26 | 2.13 | 364.8% | 1.683 | 6.0988 | 61.6% | Só Portugal — melhor relação qualidade-preço | 2.38 | CKH986 (ESIM Access)
Conforto PT (ESIM Access) | 10 | 30 dias | 14.9 | 3.8092 | 11.0908 | 74.43% | 200 | 19 | 3.2 | 365.6% | 2.533 | 8.5578 | 57.43% | Só Portugal — utilizadores frequentes | 4.28 | CKH1004 (ESIM Access)
Liberdade PT (ESIM Access) | 20 | 30 dias | 22.9 | 7.298 | 15.602 | 68.13% | 200 | 13 | 3.49 | 556.2% | 3.893 | 11.709 | 51.13% | Só Portugal — utilizadores intensivos, estadias longas | 8.2 | CKH1011 (ESIM Access)
💱 CÂMBIO USD → EUR | Taxa USD/EUR | 0.89 | ← 1 USD = ? EUR [ACTUALIZAR]
📐 GUIA DE SAÚDE DA MARGEM
< 30% margem bruta | 🔴 Zona de perigo — rever custo grossista ou aumentar preço de venda
30–49% margem bruta | 🟡 Aceitável — monitorizar com atenção, margem limitada para cobrir custos
50–65% margem bruta | 🟢 Saudável — cobre custos operacionais, suporte e investimento em marketing
> 65% margem bruta | ⭐ Excelente — forte poder de precificação ou custo grossista muito baixo
🤝 IMPACTO DA PARCERIA — COMISSÕES SOBRE VENDAS
Modelo de parceria (Proposta Maio 2026): comissão paga sobre o preço de venda em cada activação gerada via link/QR/página co-branded do parceiro. Ajuste a célula AMARELA (D46) para simular a % das vendas que passam por parceiros.
Nível | Activações / mês | Taxa de Comissão | % das Vendas via Parceiros (mix) | Taxa Efectiva Ponderada
Parceiro | 1 – 49 | 15% | 60% | 17%
Parceiro Plus | 50+ | 20% |  | ← Aplica-se ao preço de venda (Coluna D) em cada linha
Mix por defeito: 60% das vendas via parceiros (10%) + 40% directo (sem comissão equivalente a 15% Plus na ponderação acima — D47 representa o complemento). Ajuste C46, C47 e D46 conforme o seu cenário real. |  |  | 40%
💡 Como ler: a coluna G (Margem %) mostra a margem bruta antes da comissão de parceiro. A coluna N (Margem Líquida Pós-Comissão %) reflecte a margem real após pagar a comissão ao parceiro. É esta a margem que o negócio retem.
⚠️ Atenção Fase 2 (corredor PALOP): com 17% de comissão efectiva ponderada, vários planos do corredor caem para a zona vermelha/amarela. Considere: (a) renegociar custos grossistas, (b) ajustar preços de venda, ou (c) limitar parceria aos planos Portugal/Europa.

## Competitor Pricing
💰 PalopConnect — Competitor Pricing Intelligence
Benchmark pricing across all 5 PALOP markets + Portugal. Sources: eSIMDB, MyBestSIM, esims.io, Vodafone PT. Data as of May 2026.
Market | Provider | Data (GB) | Validity | Price ($) | $/GB | Plan Type | Tethering | Market Size | PalopConnect Opportunity
🇦🇴 Angola | Nomad | 3 | 30 days | 19 | 6.3333 | Fixed | ✅ Yes | 200+ plans | Most plans are expensive ($6+/GB). PalopConnect can undercut at $4-5/GB with PT-language support.
🇦🇴 Angola | GoMoWorld | 5 | 30 days | 34.81 | 6.962 | Fixed | ✅ Yes | 30+ providers | Mid-tier pricing. No Portuguese language support — clear differentiation opportunity.
🇦🇴 Angola | Roamless | 3 | No expiry | 23.85 | 7.95 | PAYG | ✅ Yes |  | No-expiry model interesting for frequent travellers. Premium price per GB.
🇦🇴 Angola | Ubigi | 1 | 7 days | 48 | 48 | Fixed | ❌ No |  | Extremely expensive — $48/GB. Proves Angola is an underserved, high-price market.
🇲🇿 Mozambique | Airalo | 5 | 15 days | 32 | 6.4 | Fixed | ✅ Yes | 1200+ plans | Airalo is the market leader. Vodacom is primary network. High plan count = saturated.
🇲🇿 Mozambique | Holafly | Unlimited | 10 days | 34.99 | N/A | Unlimited | 500MB/day |  | "Unlimited" with daily cap. PalopConnect can offer honest fixed plans with better value.
🇲🇿 Mozambique | Saily | 10 | 30 days | 16.99 | 1.699 | Fixed | ✅ Yes |  | Best value in Mozambique. Security features included (VPN). Hard to beat on price alone.
🇲🇿 Mozambique | GigSky | 1 | 7 days | 4.99 | 4.99 | Fixed | ✅ Yes |  | Apple Travel eSIM integration (1-tap install). Premium price but frictionless UX.
🇨🇻 Cape Verde | Airalo | 10 | 30 days | 49 | 4.9 | Fixed | ✅ Yes | 160+ plans | High-volume leisure corridor. $4.90/GB is premium — room for a $3-4/GB PALOP-specific play.
🇨🇻 Cape Verde | eSIM4Travel | 1 | 7 days | 10.57 | 10.57 | Fixed | ✅ Yes | 13 providers | Budget entry point. Unitel T+ is the local network. Limited provider count = less competition.
🇨🇻 Cape Verde | GlobaleSIM | 10 | 30 days | 70.4 | 7.04 | Fixed + SMS | ✅ Yes |  | Includes phone number + SMS — rare in the market. $7/GB is very high.
🇨🇻 Cape Verde | Firsty | 5 | 1 day | 3 | 0.6 | Budget | ✅ Yes |  | Cheapest entry — but 1-day validity only. Useful as price anchor for comparison.
🇬🇼 Guinea-Bissau | GlobaleSIM | 10 | 30 days | 24.8 | 2.48 | Fixed | ✅ Yes | 63 providers | Best value for GB. 562 plans but most are regional/global bundles, not GB-specific.
🇬🇼 Guinea-Bissau | Monty eSIM | 5 | 30 days | 15.99 | 3.198 | Fixed | ✅ Yes |  | Decent price point. Smaller brand — no community recognition or Portuguese support.
🇬🇼 Guinea-Bissau | Orbit Mobile | 10 | 30 days | 45 | 4.5 | Fixed | ✅ Yes |  | High-price tier. Also offers Africa Pass (39 countries) at similar rates.
🇸🇹 São Tomé e Príncipe | Nomad | 1 | 7 days | 25 | 25 | Fixed | ✅ Yes | 2 providers | 🚨 Most expensive PALOP market — $19.67/GB from Nomad. 3G only. Massive gap.
🇸🇹 São Tomé e Príncipe | Nomad | 3 | 30 days | 59 | 19.6667 | Fixed | ✅ Yes |  | 3GB/30d = $19.67/GB. Only Nomad + Roamless serve STP directly. Blue ocean.
🇸🇹 São Tomé e Príncipe | Roamless | 1 | 30 days | 25.95 | 25.95 | PAYG | ✅ Yes |  | Multi-country plan. Only viable alternative to Nomad. PalopConnect can own this market.
🇵🇹 Portugal | Airhub | 10 | 30 days | 3.49 | 0.349 | Fixed | ✅ Yes | 883+ plans | Hyper-competitive market. $0.35/GB floor. PalopConnect must compete on community value, not price.
🇵🇹 Portugal | GoMoWorld | 5 | 7 days | 2.32 | 0.464 | Fixed | ✅ Yes | 32+ providers | Sub-$1/GB pricing. This is the destination market — bundle PT with PALOP corridor plans.
🇵🇹 Portugal | eSIM4 (top pick) | Unlimited | 30 days | 29.99 | N/A | Unlimited | ✅ Yes |  | Includes PT phone number + auto-routes NOS/Vodafone/MEO. Premium but complete.
🇵🇹 Portugal | Vodafone PT Tourist | 10 | 30 days | 25 | 2.5 | Tourist SIM | ✅ Yes |  | Airport benchmark. €25 for 10GB + 500 mins. Includes calls to PALOP countries — key insight.
💸 Vodafone PT Roaming | Tarifa Diária | Plan data | Per day | 4.9 | €4.90/day | Roaming | ✅ Yes | Zone 2 only | Covers Mozambique ONLY. Angola, CV, GB, STP are Zone 4 — NOT covered. 7-day trip = €34.30.
💸 Vodafone PT Roaming | Global Daily | 50 MB | Per day | 8 | €160/GB! | Roaming | ❌ No | All PALOP | €8/day for 50MB = €160/GB effective. 7-day trip = €56 for 350MB! This is the pain PalopConnect solves.
💸 Vodafone PT Roaming | Zone 4 Base Rate | Per MB | Per use | €7.27/MB | €7,444/GB! | Base roaming | ❌ No | AO, CV, GB, STP | Without Global Daily opt-in, Zone 4 base = €7.27/MB. Bill shock territory. Strongest marketing angle.
💸 NOS / MEO Roaming | Similar Zone 3-4 | Varies | Per use | €5-8/day | Very high | Roaming | ❌ No | All PALOP | NOS & MEO have similar zone structures. All 3 PT carriers penalise PALOP roaming heavily.
💡 Key Insights — Phase 1 Findings
🎯 Market Opportunity Ranking
1. 🇸🇹 São Tomé e Príncipe — Blue ocean. Only 2 providers. $19-25/GB. PalopConnect can own this market entirely.
2. 🇦🇴 Angola — High prices ($6-48/GB), 200+ plans but no PT-language or community-focused brand. Strong differentiation.
3. 🇬🇼 Guinea-Bissau — 63 providers but mostly generic global/regional plans. No dedicated corridor brand exists.
4. 🇨🇻 Cape Verde — High-volume leisure market. Competitive ($3-10/GB) but no PALOP-specific offering.
5. 🇲🇿 Mozambique — Most competitive PALOP market. Saily at $1.70/GB is hard to beat. Win on community, not price.
6. 🇵🇹 Portugal — Hyper-competitive ($0.35/GB floor). Must bundle with PALOP corridors, not compete standalone.
💰 Pricing Anchor: The Roaming Pain Point
Vodafone PT charges €4.90/day to Mozambique, €8/day (50MB!) via Global Daily to other PALOP, or €7.27/MB base rate to Angola/CV/GB/STP.
A 7-day trip to Angola with 1GB of data via Vodafone roaming costs €56+ (Global Daily) or €7,440+ (base rate). PalopConnect at $15-25 is 70-99% cheaper.
🚀 Recommended PalopConnect Pricing Strategy
• STP/Angola/Guinea-Bissau: Price at 40-60% below cheapest competitor. No one serves these corridors with PT support.
• Cape Verde: Match mid-market ($4-5/GB) with corridor-specific branding and PT-language support as differentiator.
• Mozambique: Can't win on price alone. Lead with community trust, PT support, and corridor bundle (MZ+PT combo plan).
• Portugal: Bundle as arrival destination, not standalone product. "Chega a Portugal, já tens internet" — pre-activated on landing.
➡️ Next: Phase 2 — Segment Sizing (quantify each reader profile × corridor to size the TAM)

## Segment Sizing
📊 PalopConnect — Segment Sizing & Revenue Model (UPDATED)
This sheet is split into Phase 1 (live product — Portugal + Europe, priced in €) and Phase 2 (planned corridor plans — PALOP markets).
PHASE 1 — Portugal + Europe Arrival Plans (LIVE — May 18th Launch)
Target: PALOP diaspora & travellers arriving in Portugal who need connectivity on landing. All prices in EUR.
Plan | Data (GB) | Validity | Sell Price (€) | Est. Units — Year 1 | Revenue — Year 1 (€) | Notes
Arrival | 2 | 7 days | 3.99 | 1200 | 4788 | Great for first-time arrivals & short stays
Essential | 5 | 30 days | 9.99 | 3500 | 34965 | Sweet spot — most popular plan on site
Comfort | 10 | 30 days | 14.99 | 1800 | 26982 | Longer stays, frequent WhatsApp users
Freedom | 20 | 30 days | 19.99 | 600 | 11994 | Power users, digital nomads, long stays
TOTAL — Phase 1 |  |  |  | 7100 | 78729 | Year 1 @ conservative estimates (update units in blue cells)
ℹ️ Blue cells = editable assumptions. Update 'Est. Units' with actual targets. Revenue recalculates automatically.
PHASE 1 — Penetration Sensitivity (PT Arrival Market)
Scenario | Annual Addressable Trips | Capture Rate | eSIMs Sold | Avg Revenue/eSIM (€) | Total Revenue (€)
Conservative | 71000 | 3% | 2130 | 9.99 | 21278.7
Base Case | 71000 | 5% | 3550 | 9.99 | 35464.5
Optimistic | 71000 | 8% | 5680 | 9.99 | 56743.2
ℹ️ Phase 1 addressable trips = ~71K/yr (PALOP visitors + diaspora to PT). Avg revenue uses Essential plan price as proxy. Update blue cells.
PHASE 2 — PALOP Corridor Plans (Planned Expansion) — Original analysis below preserved. Currency: USD.
⚠️ The TAM model below ($232K Year 1) applies to corridor plans (Angola, Cape Verde, etc.) NOT to the Phase 1 live product. These plans require separate supplier coverage confirmation before launch.
📊 PalopConnect — Segment Sizing & TAM Analysis
Quantifies the addressable market per customer segment × corridor using travel, diaspora, and roaming data.
Metric | 🇦🇴 Angola | 🇲🇿 Mozambique | 🇨🇻 Cape Verde | 🇬🇼 Guinea-Bissau | 🇸🇹 STP | 🇵🇹 Portugal | Total / Notes
DIASPORA POPULATION IN PORTUGAL
Registered foreign residents (2024) | 92348 | 12000 | 66000 | 30000 | 15000 | — | 215348
Incl. naturalized & 2nd gen (est.) | 150000 | 20000 | 260000 | 50000 | 25000 | — | 5993.99
% of total PALOP in PT | 42.88% | 5.572% | 30.65% | 13.93% | 6.965% | — | 100%
CAPE VERDE DIASPORA ACROSS EUROPE
CV in Portugal (incl. descendants) | — | — | 260000 | — | — | — | Source: CV gov't estimate
CV in Netherlands |  |  | 20000 |  |  |  | Concentrated in Rotterdam
CV in France |  |  | 25000 |  |  |  | Paris region mainly
CV in Spain + Luxembourg + Italy |  |  | 25000 |  |  |  | ES 12.5K, LU 7K, IT ~5K
Total CV diaspora in Europe (est.) |  |  | 0 |  |  |  | Gov't claims ~450K in all of Europe
TRAVEL & TOURISM VOLUMES
Tourism arrivals (latest annual) | n/a | n/a | 400000 | n/a | n/a | 29000000 | CV=Q4 2025; PT=2024 total
TAP LIS direct flights to PALOP? | ✅ | ✅ | ✅ | ✅ | ✅ | Hub | All PALOP capitals via LIS
Vodafone PT roaming zone | Zone 4 🔴 | Zone 2 🟡 | Zone 4 🔴 | Zone 3 🟠 | Zone 4 🔴 | Home | Zone 4 = per-MB base rate (€€€)
Roaming cost estimate (7-day trip) | €50-100+ | €34.30 | €50-100+ | €50-100+ | €50-100+ | — | MZ only has €4.90/day; rest = per-MB
ADDRESSABLE MARKET BY SEGMENT
Seg 1: PALOP visitors to PT | ~30K | ~8K | ~25K | ~5K | ~3K | Destination | ~71K annual trips/yr (est.)
Seg 2: Portuguese to PALOP | ~25K | ~15K | ~40K | ~3K | ~5K | Origin | ~88K annual trips/yr (est.)
Seg 3: Diaspora returning to PT | ~15K | ~5K | ~50K | ~5K | ~3K | Destination | ~78K annual trips/yr (est.)
Seg 4: PALOP diaspora in EU | ~5K | ~2K | ~80K | ~2K | ~1K | Hub | ~90K trips via LIS hub/yr (est.)
TOTAL ADDRESSABLE TRIPS/YEAR | ~75K | ~30K | ~195K | ~15K | ~12K |  | ~327K total addressable trips
REVENUE OPPORTUNITY (est. Year 1 @ 5% penetration)
Addressable trips × 5% capture | 3750 | 1500 | 9750 | 750 | 600 |  | 0
Avg. revenue per eSIM sold ($) | 18 | 15 | 12 | 16 | 22 |  | Weighted avg ~$14.50
Year 1 revenue estimate ($) | 0 | 0 | 0 | 0 | 0 |  | 0
KEY INSIGHT
Cape Verde is the dominant corridor — ~60% of addressable trips come from CV diaspora & tourism. The CV-PT corridor alone justifies launch. Angola is #2 by volume + highest roaming pain (Zone 4). STP has smallest volume but highest $/unit (blue ocean pricing). Portugal is the universal arrival destination — every segment passes through LIS.

## Supply & Margin
💰 PalopConnect — Supply & Margin Analysis
Update all BLUE cells with your actual supplier wholesale costs. All margin calculations update automatically. Yellow cells = assumptions requiring attention.
PHASE 1 — Portugal + Europe Plans (Live — May 18th)
Plan | Data (GB) | Validity | Sell Price (€) | Wholesale Cost (€) [UPDATE] | Gross Margin (€/unit) | Gross Margin % | Est. Monthly Fixed Costs (€) [UPDATE] | Break-even Units/Month | Competitor Benchmark (€) | vs. Cheapest Competitor
Arrival | 2 | 7 days | 3.99 | 1.2 | 2.79 | 69.92% | 200 | 72 | 3.2 | 24.69%
Essential | 5 | 30 days | 9.99 | 2.8 | 7.19 | 71.97% | 200 | 28 | 2.13 | 369%
Comfort | 10 | 30 days | 14.99 | 4.5 | 10.49 | 69.98% | 200 | 20 | 3.2 | 368.4%
Freedom | 20 | 30 days | 19.99 | 8 | 11.99 | 59.98% | 200 | 17 | 3.49 | 472.8%
ℹ️ Wholesale costs above are ESTIMATES based on typical EU eSIM aggregator rates. Update Column E with your actual supplier invoice costs. Fixed monthly costs (Column H) = hosting + support + ops. Update to match your actuals.
PHASE 2 — PALOP Corridor Plans (Planned Expansion)
⚠️ Corridor plans require separate supplier coverage confirmation per market. Wholesale costs below are market estimates — get actual quotes before pricing.
Market | Plan Size (GB) | Validity | Recommended Sell Price (€) [UPDATE] | Est. Wholesale Cost (€) [UPDATE] | Gross Margin (€/unit) | Gross Margin % | Cheapest Competitor ($) | Coverage Confirmed? | Priority Ranking | Notes
🇸🇹 São Tomé | 3 | 30 days | 32 | 12 | 20 | 62.5% | $59 Nomad | No | 1st | Blue ocean — only 2 competitors. 3G only — confirm speed before marketing.
🇦🇴 Angola | 3 | 30 days | 14 | 5.5 | 8.5 | 60.71% | $19 Nomad | No | 2nd | Zone 4 pain point — strongest marketing story. €7,444/GB vs Vodafone.
🇨🇻 Cape Verde | 5 | 30 days | 19 | 7 | 12 | 63.16% | $49 Airalo | No | 3rd | Highest TAM (195K trips). Price at ~$19 vs Airalo $49 for 10GB.
🇬🇼 Guinea-Bis | 5 | 30 days | 12 | 4.5 | 7.5 | 62.5% | $15.99 Monty | No | 4th | Low volume, limited competition. Low-effort add-on after CV/AO.
🇲🇿 Mozambique | 5 | 30 days | 10 | 4 | 6 | 60% | $16.99 Saily | No | 5th | Most competitive market. Saily at $1.70/GB. Win on community, not price.
📐 MARGIN HEALTH GUIDE
< 30% gross margin | 🔴 Danger zone — review wholesale cost or increase sell price
30–49% gross margin | 🟡 Acceptable — monitor carefully, limited room for ops costs
50–65% gross margin | 🟢 Healthy — covers ops, support, and marketing overhead
> 65% gross margin | ⭐ Excellent — strong pricing power or very low wholesale cost

## Pre-Launch Tracker
🚀 PalopConnect — Pre-Launch Tracker ¦ Launch Date: Sunday 18 May 2026
12 days to launch from May 6th. Status: ✅ Done ¦ 🔄 In Progress ¦ ⏳ Not Started ¦ 🚨 Blocker
# | Task | Owner | Deadline | Priority | Status | Notes / Definition of Done
🚨 LAUNCH BLOCKERS — Must be done before May 18th
1 | Fix 'Portugal' tab bug on plans page | Dev | May 8 | 🚨 Critical | ⏳ Not Started | Portugal tab shows no plan cards. Fix filter logic so PT plans render correctly. Test on desktop + mobile.
2 | Complete end-to-end purchase test | Founder | May 9 | 🚨 Critical | ⏳ Not Started | Buy one plan, receive QR by email, activate on a real device. Confirm data works. Fix any gaps found.
3 | Confirm supplier eSIM delivery is automated | Founder | May 9 | 🚨 Critical | ⏳ Not Started | Verify QR delivery is triggered instantly on payment. Test with real card. No manual steps in the flow.
4 | Fill in actual wholesale costs in Supply & Margin sheet | Founder | May 10 | 🚨 Critical | ⏳ Not Started | Update all yellow cells in Supply & Margin tab with real supplier costs. Confirm margin ≥40% on all plans.
📣 PRE-LAUNCH SEEDING — Days 1–12 (May 6–17)
5 | List 15 PALOP diaspora WhatsApp & Facebook groups | Founder | May 7 | 🔴 High | ⏳ Not Started | Find groups: Angolanos em Portugal, Cabo-Verdianos em Lisboa, Moçambicanos PT, students. Min 500 members each.
6 | Write pre-launch teaser message (PT + EN) | Founder | May 8 | 🔴 High | ⏳ Not Started | Short message: 'Lançamento 18 Mai — eSIM feito para a diáspora PALOP. Fica atento.' No link yet. Build curiosity.
7 | Post teaser in 10+ community groups (PT language) | Founder | May 10–12 | 🔴 High | ⏳ Not Started | Post in all identified groups. Track responses and DMs — these are warm buyers. Reply to every comment.
8 | Prepare launch announcement post (PT + EN) | Founder | May 14 | 🔴 High | ⏳ Not Started | Full launch post with: price, how it works, buy link, activation steps. Ready to post May 18th morning.
9 | Create Angola roaming pain point graphic | Founder/Design | May 14 | 🟡 Medium | ⏳ Not Started | 'Vodafone cobra €7.27/MB em Angola. PalopConnect: 3GB por €14. Activa em minutos.' WhatsApp-shareable image.
10 | Identify 2 diaspora association / reseller contacts | Founder | May 15 | 🟡 Medium | ⏳ Not Started | Not a sales call yet. Just a warm intro: 'We're launching, would love your input.' Reseller pitch comes post-launch.
11 | Schedule Instagram + Facebook launch posts | Founder | May 17 | 🔴 High | ⏳ Not Started | Schedule posts for May 18th 2pm PT time. Include: launch graphic, product demo story, Essential plan highlight.
🎯 LAUNCH DAY — Sunday 18 May 2026
12 | Post launch announcement in all groups (2pm PT) | Founder | May 18 | 🚨 Critical | ⏳ Not Started | Fire all scheduled posts simultaneously. Drop the buy link. Reply to every message within 1 hour.
13 | Send launch WhatsApp to personal network | Founder | May 18 | 🔴 High | ⏳ Not Started | Personal message to 50+ contacts: 'Acabámos de lançar — partilha com quem precisar.' Warm referrals are Day 1 sales.
14 | Monitor purchase flow for the first 12 hours | Founder | May 18 | 🚨 Critical | ⏳ Not Started | Watch for: failed payments, undelivered QR codes, activation errors. Fix immediately. First impressions = reviews.
15 | Post live social proof as orders come in | Founder | May 18 | 🟡 Medium | ⏳ Not Started | If you get your first sale, post it: 'Primeiro eSIM activado! Obrigado 🙏' Builds real-time momentum.
📈 POST-LAUNCH QUICK WINS — May 19–25
16 | Contact every buyer personally to confirm activation | Founder | May 19–20 | 🔴 High | ⏳ Not Started | DM or WhatsApp every buyer: 'Correu tudo bem?' Collect 3 written testimonials for the site.
17 | Add testimonials to homepage | Dev/Founder | May 21 | 🟡 Medium | ⏳ Not Started | Even 2–3 short quotes from real buyers significantly increase conversion rate for subsequent visitors.
18 | Review conversion data — which plan sold most? | Founder | May 22 | 🟡 Medium | ⏳ Not Started | Check which plan dominated. If Arrival plan outsells Essential 2:1 — adjust pricing or copy to upsell.
19 | Book first reseller meeting | Founder | May 22 | 🟡 Medium | ⏳ Not Started | Follow up on pre-launch contacts. Offer 10–15% commission per sale. One active reseller = 5–10× your reach.
📊 LAUNCH READINESS SUMMARY
Total tasks | 19
✅ Done | 0
🔄 In Progress | 0
⏳ Not Started | 19
🚨 Blockers | 6

## Data Sources
🚨 LAUNCH BLOCKER — Fix before May 18th
BUG: The 'Portugal' tab on palopconnect.com/plans shows NO plan cards — the Featured Plans section is empty when Portugal is selected. Visitors clicking 'Portugal' see a blank section before the comparison table. Fix the tab filter logic before May 18th launch.
📊 PalopConnect — Data Sources & Competitive Intelligence
Use this tracker to manage research sources for customer segment analysis and plan creation. Filter by Priority or Status to focus your workflow.
# | Priority | Source Type | Title | Link / Location | Why It Matters | What to Extract | Status
1 | 🔴 High | 📁 Internal | PALOP Roaming eSIM Marketing Initiative | Internal file | Core strategy document for the business model and target audience | Target users, pricing logic, aggregator strategy, value proposition | ⭐ Key Source
2 | 🔴 High | 📁 Internal | Roaming Travelers in PALOP Countries — 2023 Analysis | Internal file | Best source for market sizing and travel flows across PALOP corridors | Visitor numbers, destination priority, country-by-country demand | ⭐ Key Source
3 | 🔴 High | 🌐 Web | eSIMDB — Angola | https://esimdb.com/angola | Benchmark pricing and plan variety for Angola — a primary PALOP market | GB tiers, validity periods, cheapest plan, best-value plan | ⏳ Pending
4 | 🔴 High | 🌐 Web | Best eSIM Card for Mozambique — 2025 Comparison | https://mybestsim.com/en/comparison-best-esim-card-mozambique/ | Price-per-GB comparisons for Mozambique corridor planning | Entry pricing, 30-day options, unlimited vs capped plans | ⏳ Pending
5 | 🔴 High | 🌐 Web | Compare Travel eSIMs for Cape Verde | https://esimdb.com/cape-verde | Cape Verde is a high-volume leisure market — critical for plan design | Cheapest plans, top providers, regional suitability | ⏳ Pending
6 | 🟡 Medium | 🌐 Web | Best eSIM for Portugal — 2026 | https://esims.io/countries/portugal | Defines Lisbon acquisition landscape and first-stop usage patterns | Tourist plan pricing, validity norms, data buckets | ⏳ Pending
7 | 🟡 Medium | 🌐 Web | Prepaid SIM Card at Lisbon Airport — 2025 Guide | https://www.traveltomtom.net/destinations/europe/portugal/sim-card-lisbon-airport | Airport purchase behavior and price anchors for arriving travellers | On-arrival convenience, pricing, retail options | ⏳ Pending
8 | 🟡 Medium | 🌐 Web | SIM Card in Lisbon — Best 2025 Buying Tips from Locals | https://portugalesim.com/sim-cards/lisbon/ | Local benchmark for what travellers expect and what they actually pay | Tourist-friendly offers, setup friction, value messaging | ⏳ Pending
9 | 🟢 Low | 🌐 Web | Best eSIM for Portugal — Compared & Tested 2026 | https://www.traveltomtom.net/destinations/europe/portugal/best-esim-cards-for-portugal | Strong best-value framing reference for a mature travel market | How providers position value, low-cost tiers, comparison method | ⏳ Pending
10 | 🟢 Low | 🌐 Web | Top eSIM Providers for Portugal — Ranked 2026 | https://www.esim4.com/blog/best-esim-for-portugal/ | Comparator for plan framing and customer language competitors use | Provider ranking logic, traveller pain points, offer structure | ⏳ Pending
11 | 🔴 High | 🌐 Web | eSIMDB — Guinea-Bissau | https://esimdb.com/guinea-bissau | Fills the Guinea-Bissau gap — one of five PALOP markets with zero current coverage | Plan availability, provider count, pricing vs other PALOP markets | ⏳ Pending
12 | 🔴 High | 🌐 Web | eSIMDB — São Tomé e Príncipe | https://esimdb.com/sao-tome-and-principe | Completes the five PALOP markets — STP is niche but essential for brand credibility | Plan availability, pricing, whether providers even cover STP | ⏳ Pending
13 | 🔴 High | 📊 Data | Observatório da Emigração — Comunidades PALOP em Portugal | https://observatorioemigracao.pt | Diaspora size and distribution data — essential for customer segment sizing | PALOP population in Portugal by nationality, city distribution, growth trends | ⏳ Pending
14 | 🔴 High | 📊 Data | INE Portugal — Foreign Residents Statistics | https://www.ine.pt | Official Portuguese statistics on PALOP-origin residents — authoritative segment sizing | Resident permits by nationality, annual arrivals, age/city demographics | ⏳ Pending
15 | 🔴 High | 🏆 Competitor | Airalo — Angola & Cape Verde Plans | https://www.airalo.com | Market leader in travel eSIM — direct competitor for every PALOP corridor | PALOP-specific plans, pricing, UX flow, marketing language, app ratings | ⏳ Pending
16 | 🟡 Medium | 🏆 Competitor | Holafly — Unlimited eSIM Plans for Africa | https://esim.holafly.com | Unlimited-data positioning — strong brand in PT-speaking markets (BR presence) | Unlimited tier pricing, PALOP coverage gaps, PT-language marketing approach | ⏳ Pending
17 | 🟡 Medium | 💰 Roaming | Vodafone PT / NOS / MEO — Roaming Rates to PALOP | https://www.vodafone.pt / nos.pt / meo.pt | The “before” price anchor — what customers currently pay for roaming in PALOP countries | Per-MB/day roaming rates to Angola, CV, Moz; bundle options; fair-use caps | ⏳ Pending
18 | 🟡 Medium | 💰 Roaming | Unitel Angola / CVMóvel / Tmcel Moz — Outbound Roaming | https://www.unitel.ao / cvmovel.cv / tmcel.mz | PALOP-side roaming costs — what travellers from Angola/CV/Moz pay to roam in Europe | Outbound roaming rates to Portugal/EU, prepaid roaming bundles, data caps | ⏳ Pending
19 | 🟡 Medium | ⭐ Reviews | App Store & Google Play — Airalo / Holafly Reviews | App Store + Google Play search | Real customer language and friction points — gold for messaging and onboarding | Top complaints, praise themes, activation friction, PALOP-specific mentions | ⏳ Pending
Summary
Total Sources | 18
🔴 High Priority | 10
🟡 Medium Priority | 4
🟢 Low Priority | 2
⏳ Still Pending | 14
✅ Reviewed | 0

## YouTube Sources
🎬 PalopConnect — YouTube Video Sources & Competitor Content
Track YouTube search queries to monitor competitor content, customer language, and onboarding patterns across PALOP corridors.
# | Priority | Content Type | Search Query | YouTube Link | Why It Matters | Status
1 | 🔴 High | 🎥 Review | Cape Verde eSIM review | https://www.youtube.com/results?search_query=Cape+Verde+eSIM+review | Traveler reviews and setup walkthroughs — real user language and pain points | ⏳ Pending
2 | 🔴 High | 🌍 Destination | Angola eSIM travel | https://www.youtube.com/results?search_query=Angola+eSIM+travel | Destination-specific usage insights for Angola — a primary PALOP market | ⏳ Pending
3 | 🔴 High | 🌍 Destination | Mozambique eSIM travel | https://www.youtube.com/results?search_query=Mozambique+eSIM+travel | Destination-specific usage insights for Mozambique corridor | ⏳ Pending
4 | 🔴 High | 🚿 Local | Lisbon SIM card for tourists | https://www.youtube.com/results?search_query=Lisbon+SIM+card+for+tourists | Local acquisition behavior — how tourists currently buy connectivity on arrival | ⏳ Pending
5 | 🟡 Medium | 🔍 Comparison | Portugal eSIM comparison | https://www.youtube.com/results?search_query=Portugal+eSIM+comparison | Market benchmarks and plan framing — how competitors position value | ⏳ Pending
6 | 🟡 Medium | 💡 Strategy | How to avoid roaming charges in Africa | https://www.youtube.com/results?search_query=How+to+avoid+roaming+charges+in+Africa | Value proposition validation — confirms the pain point PalopConnect solves | ⏳ Pending
7 | 🟡 Medium | 🏆 Competitor | Best eSIM for Cape Verde | https://www.youtube.com/results?search_query=Best+eSIM+for+Cape+Verde | Competitor positioning — who’s winning Cape Verde search visibility | ⏳ Pending
8 | 🟡 Medium | 🏆 Competitor | Best eSIM for Portugal | https://www.youtube.com/results?search_query=Best+eSIM+for+Portugal | Competitor positioning — who’s dominating Portugal search results | ⏳ Pending
9 | 🟢 Low | 🌍 Destination | Best travel eSIM Africa | https://www.youtube.com/results?search_query=Best+travel+eSIM+Africa | Regional product context — broader Africa eSIM landscape for positioning | ⏳ Pending
10 | 🟢 Low | 🛠️ Tutorial | eSIM setup tutorial iPhone Android travel | https://www.youtube.com/results?search_query=eSIM+setup+tutorial+iPhone+Android+travel | Onboarding friction and UX cues — what confuses users during activation | ⏳ Pending
11 | 🔴 High | 🇵🇹 PT-PT | eSIM para viajar para Angola | https://www.youtube.com/results?search_query=eSIM+para+viajar+para+Angola | PT-PT search — surfaces content your actual customer audience watches and shares | ⏳ Pending
12 | 🔴 High | 🇵🇹 PT-PT | chip para turista em Portugal | https://www.youtube.com/results?search_query=chip+para+turista+em+Portugal | PT-PT arrival query — how Portuguese-speaking travellers search for connectivity | ⏳ Pending
13 | 🔴 High | 🇵🇹 PT-PT | como funciona eSIM viagem internacional | https://www.youtube.com/results?search_query=como+funciona+eSIM+viagem+internacional | PT-PT education query — reveals what confuses lusophone users about eSIM | ⏳ Pending
14 | 🟡 Medium | 🇵🇹 PT-PT | internet em Cabo Verde para turistas | https://www.youtube.com/results?search_query=internet+em+Cabo+Verde+para+turistas | PT-PT Cape Verde query — high-volume leisure market in the customer’s language | ⏳ Pending
15 | 🟡 Medium | 🇵🇹 PT-PT | evitar roaming África viagem | https://www.youtube.com/results?search_query=evitar+roaming+%C3%81frica+viagem | PT-PT pain point query — mirrors the EN roaming avoidance query for lusophone audience | ⏳ Pending
16 | 🟡 Medium | 🇵🇹 PT-PT | eSIM Moçambique internet | https://www.youtube.com/results?search_query=eSIM+Mo%C3%A7ambique+internet | PT-PT Mozambique query — corridor-specific content in the customer’s language | ⏳ Pending
Summary
Total Queries | 16
🔴 High Priority | 7
🟡 Medium Priority | 7
🟢 Low Priority | 2
⏳ Still Pending | 16
✅ Reviewed | 0